## Sheet1
PERT Analysis Table A -- For your project
NOTE: Timeframe to use is your choice – here it is days, make the changes as appropriate to your project.
A | B | C |  |  | D | E | F (optional) | G | H
(optional)
List of activities | Activity numbers | Duration in Days |  |  | Te | TE | TL | Slack | Variance of te
|  | A optimistic | M mode | B pessimistic | =(a+4m+b)/6 | Take largest | Take smallest | TL-TE | = ((b-a)/6)2
Staff recruiting | 0-1 | 10 | 14 | 20 | 14.3333 | 14.6667 | 10 | 4.6667 | 2.7778
Facility Recrutment | 1 to 2 | 4 | 6 | 8 | 6 | 6 | 4 | 2 | 0.44444
Staff Training | 2 to 3 | 0.3 | 0.5 | 1 | 0.55 | 0.6 | 0.3 | 0.3 | 0.013611
Facility Staff Training | 3 to 4 | 0.3 | 0.5 | 1 | 0.55 | 0.6 | 0.3 | 0.3 | 0.013611
Patient Recruitment | 4 to 9 | 365 | 365 | 380 | 367.5 | 370 | 365 | 5 | 6.25
Patient Pre-testing interviews | 4 to 5 | 0.1 | 0.4 | 8 | 1.6167 | 2.8333 | 0.1 | 2.7333 | 1.7336
Patient Test Resulting | 5 to 6 | 3 | 5 | 10 | 5.5 | 6 | 3 | 3 | 1.3611
Patient interviews | 6 to 7 | 1 | 5 | 10 | 5.1667 | 5.3333 | 1 | 4.3333 | 2.25
Records Processing | 7 to 8 | 1 | 5 | 10 | 5.1667 | 5.3333 | 1 | 4.3333 | 2.25
Data Entering | 10 to 11 | 7 | 14 | 30 | 15.5 | 17 | 7 | 10 | 14.6944
Data Check | 11 to 10 or 10 to 11 | 7 | 14 | 30 | 15.5 | 17 | 7 | 10 | 14.6944
Data Analysis | 11 to 12 | 20 | 60 | 90 | 58.3333 | 56.6667 | 20 | 36.6667 | 136.1111
["te" is the average duration of an activity]
Draw your network with the critical path highlighted. PLEASE NOTE: you must have at least one set of parallel activities in your PERT.